## Sheet1
Saccoccio & Associates Architects East Greenwich Schools RIDE Capital Improvement Plan
| School Name/Category |  | Description of work | Category | Priorities |  | Construction Cost |  | 5 Year Capital Plan |  |  |  |  | Total | Description of Project
[5 empty] | Jacob's | District |  |  | 2017 | 2018 | 2019 | 2020 | 2021
| COLE | Exterior | Replace tennis courts | Capital Renewal | NA | 1 | [6 empty] | 400000 | 400000 | Tennis courts need to be fully excavated to a depth of 4', the unsuitable fill must be removed, and the courts reconstucted
| COLE | Mechanical | DDC to control Summer Mode |  | na | 2 |  | 30000 |  |  | 30000 |  |  | 30000 | Mechanical system programing to attain a minimal level of buiding cooling in the summer months
| COLE | Security 1 | Archie Cole Middle School |  | na | 1 | 0 | 57500 |  |  | 40000 |  |  | 40000 | Security upgrade details are confidential
| COLE | Security 2 | Archie Cole Middle School |  | na | 2 | 0 | 57500 |  |  | 30000 |  |  | 30000 | Security upgrade details are confidential
| COLE | Network | Replace/ Upgrade Switches | Capital Renewal |  | 2 | [6 empty] | 25000 | 25000 | Replace and upgrade end of life switches
| COLE | Network | Replace/ Upgrade Servers | Capital Renewal |  | 2 | [6 empty] | 60000 | 60000 | Replace and upgrade end of life servers
| COLE | Network | Replace/upgrade Wireless A.P | I.T. End of life | na | 1 |  |  |  |  | 66000 |  |  | 66000 | Replace and upgrade end of life wireless access points
| COLE | Network | Replace /upgrade IP Phones | I.T. End of life | na | 1 |  |  |  |  | 32000 |  |  | 32000 | Replace and upgrade end of life ip phones
| COLE | Specialties | Custodial Equipmet |  | na | 3 |  |  |  |  | 10000 |  | 10000 | 20000 | Replacing / upgrading the District's 20 yr old custodial equipment
|  |  | Archie Cole School Subtotal | [7 empty] | 208000 | 0 | 95000 | 703000
| DIST | Specialties | Replace SD-4 |  | na | 1 | 0 | 57500 |  |  | 70000 |  |  | 70000 | Replacing District maintenance vehichles with comparable f-550's with plows. Used for snow operations by the town
| DIST | Specialties | Replace SD-3 |  | na | 1 | 0 | 57500 |  |  | 70000 |  |  | 70000 | Replacing District maintenance vehichles with comparable f-550's with plows. Used for snow operations by the town
| DIST | Specialties | Replace SD-2 |  | na | 2 | 0 | 57500 |  |  |  | 70000 |  | 70000 | Replacing District maintenance vehichles with comparable f-550's with plows. Used for snow operations by the town
| DIST | Specialties | Replace SD-1 |  | na | 2 | 0 | 57500 |  |  |  | 70000 |  | 70000 | Replacing District maintenance vehichles with comparable f-550's with plows. Used for snow operations by the town
| DIST | Specialties | Replace SD-5 |  | na | 2 | 0 | 57500 |  |  |  | 40000 |  | 40000 | Replacing District maintenance vehichles with comparable f-550's with plows. Used for snow operations by the town
|  |  | Maintenance Subtotal | [7 empty] | 140000 | 180000 | 0 | 320000
| EGHS | Electrical | Replace equipment | Capital Renewal | 2 | 2 | 447963 | 447963 |  |  | 44275 | 77625 |  | 121900 | Replace mainline switches, distribution panels and sub panels, to remove the threat of electrical fire and rebalance loads and space
| EGHS | Exterior | Caulk Exterior Joints |  | na | 1 | 0 | 34500 |  |  | 34500 |  |  | 34500 | Prevent Moisture, bugs, and rodents from accessing the façade
| EGHS | Exterior | Paint Exterior Soffits |  | na | 3 | 0 |  |  |  | 28750 |  |  | 28750 | Prevent Moisture, bugs, and rodents from accessing the façade
| EGHS | Fire and Life Safety | 2nd Exit From Boiler Room |  | na | 1 | 0 | 57500 |  |  | 57500 |  |  | 57500 | Modifications to the boiler room to create a 2nd means of egress from the boiler "pit"
| EGHS | Fire and Life Safety | Boiler Room Enclosure |  | na | 1 |  | 46000 |  |  | 52000 |  |  | 52000 | Modifications to the boiler room to maintain the ceiling fire rating
| EGHS | Fire and Life Safety | Dead End Cooridor |  | na | 1 | 0 | 23000 |  |  | 23000 |  |  | 23000 | Modifications to the boiler room to eliminate dead end cooridor fire trap
| EGHS | Fire and Life Safety | Fire sprinklers | Code Compliance | 3 | 1 | 2400954 | 2400954 |  |  |  |  | 28750 | 28750 | Installing local domestic sprinklers in storage closets and mechanical rooms to comply with firecode
| EGHS | Fire and Life Safety | Railings |  | na | 1 | 0 | 33925 |  |  | 33925 |  |  | 33925 | Install railings in room 131 "the pit" which is not ADA Compliant
| EGHS | Interior | Replace doors | Capital Renewal | 3 | 1 | 862235 | 862235 |  |  | 28750 |  |  | 28750 | Replace lower level interior vestibule doors with fire rated
| EGHS | Interior | Sound control | Capital Renewal | 3 | 1 |  |  |  |  | 11500 |  |  | 11500 | Music room requires additional acoustical sound attenuation to enhance educational quality
| EGHS | Interior | Replace Cabinetry | Capital Renewal | 3 | 3 |  |  |  |  | 33062 |  |  | 33062 | Replace the built-in cabinetry in the ceramics suite
| EGHS | Interior | Network moisture protection |  | na | 2 |  |  |  |  | 50000 |  |  | 50000 | Network closets are located next to and underneath existing bathrooms
| EGHS | Mechanical | Replace equipment | Capital Renewal | 2 | 2 | 3383348 | 3383348 |  |  | 158700 | 5750 |  | 164450 | Replacing major pieces of air handling/heat distribution equipment for common spaces, old gym, cafeteria, and theater
| EGHS | Plumbing | ADA | Barrier to accessibility | 3 | 2 | 139437 | 139437 |  |  | 6900 | 5750 | 59225 | 71875 | Modify existing student bathrooms for proper accessibilty
| EGHS | Plumbing | Replace Fixtures | Capital Renewal | 2 | 2 | 205525 | 205525 |  |  | 35937 |  | 44275 | 80212 | Replacing the original toilets, urinals, and lavatories
| EGHS | Site | Improve landscaping at the perimeter | Capital Renewal | 2 | 3 | [5 empty] | 28750 |  | 28750 | Remove dead trees and live vegetation off the "teachers" road and at building perimeter
| EGHS | Site | Paving | Capital Renewal | 2 | 1 | 585822 | 585822 |  |  |  | 57500 |  | 57500 | Repaving the "teachers road" and parking along the side of the building
| EGHS | Security 1 | East Greenwich High School |  | na | 1 | 0 | 57500 |  |  | 145000 |  |  | 145000 | Security upgrade details are confidential
| EGHS | Security 2 | East Greenwich High School |  | na | 2 | 0 | 57500 |  |  | 58000 |  |  | 58000 | Security upgrade details are confidential
| EGHS | Network | Replace/ Upgrade Switches | Capital Renewal |  | 2 | [6 empty] | 70000 | 70000 | Replace and upgrade end of life switches
| EGHS | Network | Replace/ Upgrade Servers | Capital Renewal |  | 2 | [6 empty] | 60000 | 60000 | Replace and upgrade end of life servers
| EGHS | Network | Upgrade Sans | Capital Renewal |  | 3 |  |  |  |  | 50000 |  |  | 50000 | Replace and upgrade end of life servers
| EGHS | Network | Instructional IT Rewiring | Capital Renewal |  | 3 | [6 empty] | 60000 | 60000 | Replace and upgrade wiring to facilitate technology
| EGHS | Network | Replace/upgrade Wireless A.P | I.T. End of life | na | 1 |  |  |  |  | 78000 |  |  | 78000 | Replace and upgrade end of life wireless access points
| EGHS | Network | Replace /upgrade IP Phones | I.T. End of life | na | 1 |  |  |  |  | 24000 |  |  | 24000 | Replace and upgrade end of life ip phones
| EGHS | Specialties | Custodial Equipmet |  | na | 3 |  |  |  |  | 10000 |  | 10000 | 20000 | Replacing /upgrading the District's 20 yr old custodial equipment
|  |  | East Greenwich High School Subtotal | [7 empty] | 963799 | 175375 | 332250 | 1471424
| ELD | Electrical | Replace equipment | Capital Renewal | 2 | 2 | 60310 | 90275 |  |  | 31625 | 58650 |  | 90275 | Replace mainline switches, distribution panels, and sub panels to remove the threat of electrical fire and rebalance loads
| ELD | Fire and Life Safety | code | code | 0 | 1 | 0 | 43125 |  |  | 36225 |  |  | 36225 | Replace existing corridor "office" walls with full height for fire seperation
| ELD | Interior | Ceilings | Acoustical | 4 | 1 | 50831 | 800000 |  |  |  | 13000 |  | 13000 | Replace the acoustical ceiling tiles in 6 ofices
| ELD | Interior | Carpeting | Capital Renewal | 3 | 3 | [5 empty] | 38570 |  | 38570 | Replace the carpeting throught
| ELD | Interior | Doors and Hardware |  | 0 | 1 | 0 | 100000 |  |  |  |  | 6900 | 6900 | Replace the fire rated pair of doors at the gym
| ELD | Mechanical | Add AC to library and Data | Building Use | 0 | 2 | 0 | 13625 |  |  | 13625 |  |  | 13625 | Adding air-conditioning to server rooms to prevent necessary IT equipment from over-heating
| ELD | Site | Modify Bathrooms for HC compliance | Accessability | na | 1 | 0 | 34500 |  |  | 34500 |  |  | 34500 | Modify existing student bathrooms for proper accessibilty
| ELD | Site | Exterior Door and Stair from Caf | Accessability | na | 1 | 0 |  |  |  | 17250 |  |  | 17250 | Replace existing exterior egress door that does not meet curent building code
| ELD | Site | Replace Playground equipment | Athletics | na | 1 | 0 | 30000 |  |  | 40000 |  |  | 40000 | Replace existing elementry playground structures that do not meet current saftey standards.
| ELD | Security 1 | Eldredge |  | na | 1 | 0 | 57500 |  |  | 72000 |  |  | 72000 | Security upgrade details are confidential
| ELD | Security 2 | Eldredge |  | na | 2 | 0 | 57500 |  |  | 25000 |  |  | 25000 | Security upgrade details are confidential
| ELD | Network | Replace/ Upgrade Switches | Capital Renewal |  | 2 | [6 empty] | 10000 | 10000 | Replace and upgrade end of life switches
| ELD | Network | Replace/upgrade Wireless A.P | I.T. End of life | na | 1 |  |  |  |  | 30000 |  |  | 30000 | Replace and upgrade end of life wireless access points
| ELD | Network | Replace /upgrade IP Phones | I.T. End of life | na | 1 |  |  |  |  | 11000 |  |  | 11000 | Replace and upgrade end of life ip phones
| ELD | Specialties | Custodial Equipmet |  | na | 3 | [6 empty] | 20000 | 20000 | Replacing /upgrading the District's 20 yr old custodial equipment
|  |  | Eldredge School Subtotal | [7 empty] | 311225 | 110220 | 36900 | 458345
| FRT | Electrical | Additional Circuits to classrooms |  | na | 1 | 0 | 34500 |  |  | 34500 |  |  | 34500 | Running additional circuits for additional classroom outlets to facilitate technology
| FRT | Electrical | Replace equipment | Capital Renewal | 2 | 2 | 67077 | 52900 |  |  |  | 28750 | 24150 | 52900 | Replace mainline switches, distribution panels, and sub panels to remove the threat of electrical fire and rebalance loads
| FRT | Exterior | Exterior Soffit | Capital Renewal | 5 | 1 | 65484 | 28750 |  |  | 28750 |  |  | 28750 | Replacing rotted soffit fascia boards
| FRT | Exterior | Replace Ice Guards |  | na | 1 | 0 | 34500 |  |  | 34500 |  |  | 34500 | Replacing the original ice/snow guards on classroom pod roofs where they have been destroyed
| FRT | Fire and Life Safety | Fire safety | Code Compliance | na | 1 | 0 | 420158 |  |  | 23000 |  | 34500 | 57500 | Installing local domestic sprinklers in storage closets and mechanical rooms per firecode; installing a fire shutter between the kitchen and cafeteria
| FRT | Mechanical | Replace Air Handling Equipment |  | na | 1 | 0 | 388250 |  |  | 40250 | 40250 |  | 80500 | Replacing major pieces of air handling and heat distribution equipment for classrooms
| FRT | Mechanical | Replace Boiler Room Equipment |  | na | 1 | 0 | 230703 |  |  | 15000 | 17250 |  | 32250 | Replacing the expansion tanks and hot water heater, and relocating the fresh air intake for the kitchen/cafeteria
| FRT | Mechanical | Replace UV | Capital Renewal | 3 | 2 | 84574 | 27025 |  |  | 14755 |  | 17250 | 32005 | Replace Kindergarten unit ventilator
| FRT | Mechanical | Replace plumbing fixtures | Educational Adequacy | 3 | 3 |  |  |  |  | 52057 |  |  | 52057 | Replacing the original toilets, urinals, and lavatories
| FRT | Site | Play Area paving | Capital Renewal | 4 | 1 | 46007 | 46007 |  |  |  |  | 46000 | 46000 | Repaving/modification to the existing "blacktop" play area
| FRT | Specialties | Classroom Cabinetry /casework | Capital Renewal | 4 | 1 | 246132 | 297000 |  |  | 181125 |  |  | 181125 | Replacing the existing wooden built-in in classrooms, Pod
| FRT | Specialties | Common Area casework |  | na | 1 | 0 | 72450 |  |  | 72450 |  |  | 72450 | Replacing the existing cafeteria tables
| FRT | Specialties | Library Casework |  | na | 1 | 0 | 28750 |  |  |  |  | 28750 | 28750 | Replacing the existing wooden library shelving/storage
| FRT | Site | Replace Playground Equipment | Capital Renewal | na | 1 | 0 | 30000 |  |  | 40000 |  |  | 40000 | Replace existing elementry playground structures that do not meet current saftey standards
| FRT | Security 1 | Frenchtown |  | na | 1 | 0 | 57500 |  |  | 81000 |  |  | 81000 | Security upgrade details are confidential
| FRT | Security 2 | Frenchtown |  | na | 2 | 0 | 57500 |  |  | 25000 |  |  | 25000 | Security upgrade details are confidential
| FRT | Network | Replace/ Upgrade Switches | Capital Renewal |  | 2 | [6 empty] | 7000 | 7000 | Replace and upgrade end of life switches
| FRT | Network | Replace/upgrade Wireless A.P | I.T. End of life | na | 1 |  |  |  |  | 24000 |  |  | 24000 | Replace and upgrade end of life wireless access points
| FRT | Network | Replace /upgrade IP Phones | I.T. End of life | na | 1 |  |  |  |  | 11000 |  |  | 11000 | Replace and upgrade end of life ip phones
| FRT | Specialties | Custodial Equipmet |  | na | 3 | [5 empty] | 10000 | 10000 | 20000 | Replacing /upgrading the District's 20 yr old custodial equipment
|  |  | Frenchtown School Subtotal | [7 empty] | 677387 | 96250 | 167650 | 941287
| HAN | Electrical | Add Surge Protection |  | na | 1 |  | 57500 |  |  | 57500 |  |  | 57500 | Install builing surge protection to prevent critical building components from being destroyed during an electical storm/power surge
| HAN | Electrical | Replace equipment | Capital Renewal | 2 | 2 | 104096 | 23000 |  |  | 17250 | 5750 |  | 23000 | Replace mainline switches, distribution panels, and sub panels to remove the threat of electrical fire and rebalance loads
| HAN | Fire and Life Safety | Install Sprinklers |  | na | 1 |  | 195563 |  |  |  |  | 17250 | 17250 | Installing local domestic sprinklers in storage closets and mechanical rooms per firecode
| HAN | Mechanical | AC in Datat Closet |  | na | 2 |  | 5000 |  |  | 5000 |  |  | 5000 | Adding air-conditioning to server rooms to prevent necessary IT equipment from over-heating
| HAN | mechanical | Replace Kitchen Hood and Exhaust |  | na | 1 |  | 40250 |  |  | 40250 |  |  | 40250 | Replace kitchen hood with new gas-fired makeup air hood unit to prevent negative building pressure
| HAN | Site | Replace Perimeter Fencing |  | na | 1 |  | 40000 |  |  |  |  | 40000 | 40000 | Replace and add to the existing perimeter fencing
| HAN | Site | Replace Sidewalk at Entrance Drive |  | na | 1 |  | 17250 |  |  | 17250 |  |  | 17250 | Remove existing curb stops and install sidewalks at entrance drive between drop-off circle and middle road
| HAN | Specialties | Cafeteria Tables |  | na | 1 |  | 55200 |  |  | 55200 |  |  | 55200 | Replacing the existing cafeteria tables
| HAN | Specialties | Replace Classrom Cabinetry | Capital Renewal | 4 | 1 | 179005 | 141450 |  |  | 141450 |  |  | 141450 | Replacing the existing wooden built-in classroom, Pod
| HAN | Site | Replace Playground Equipment |  | na | 1 |  | 30000 |  |  |  | 40000 |  | 40000 | Replace existing elementry playground structures that do not meet current saftey standards
| HAN | Security 1 | Hanaford |  | na | 1 | 0 | 57500 |  |  | 72000 |  |  | 72000 | Security upgrade details are confidential
| HAN | Security 2 | Hanaford |  | na | 2 | 0 | 57500 |  |  | 25000 |  |  | 25000 | Security upgrade details are confidential
| HAN | Network | Replace/ Upgrade Switches | Capital Renewal |  | 2 | [6 empty] | 7000 | 7000 | Replace and upgrade end of life switches
| HAN | Network | Replace/upgrade Wireless A.P | I.T. End of life | na | 1 |  |  |  |  | 25000 |  |  | 25000 | Replace and upgrade end of life wireless access points
| HAN | Network | Replace /upgrade IP Phones | I.T. End of life | na | 1 |  |  |  |  | 10000 |  |  | 10000 | Replace and upgrade end of life ip phones
| HAN | Specialties | Custodial Equipmet |  | na | 3 | [6 empty] | 20000 | 20000 | Replacing /upgrading the District's 20 yr old custodial equipment
|  |  | Hanaford School Subtotal | [7 empty] | 465900 | 45750 | 84250 | 595900
| MBK | Electrical | Additional Outlets | Educational Adequacy | 5 | 1 | 35923 | 36225 |  |  |  | 34500 |  | 34500 | Running additional circuits for additional classroom outlets to facilitate technology
| MBK | Exterior | Patch Caulk and Paint Perimeter Soffit | Capital Renewal | na | 1 | 0 | 25300 |  |  | 13800 |  | 11500 | 25300 | Prevent moisture, bugs, and rodents from accessing the facade
| MBK | Fire and Life Safety | Install Sprinklers | Capital Renewal | na | 1 | 0 | 252776 |  |  | 13800 |  |  | 13800 | Installing local domestic sprinklers in storage closets and mechanical rooms per firecode
| MBK | Fire and Life Safety | Replace Emergency lights | Capital Renewal | na | 1 | 0 | 5520 |  |  | 5520 |  |  | 5520 | Replacing the existing original grouped battery powered emergency lights with new battery LED
| MBK | Mechanical | AC Data Closet | Capital Renewal | na | 2 | 0 | 5000 |  |  | 5000 |  |  | 5000 | Adding air-conditioning to server rooms to prevent necessary IT equipment from over-heating
| MBK | Plumbing | Replace Plumbing Fixtures | Capital Renewal | 3 | 3 | 0 |  |  |  | 68738 |  |  | 68738 | Replacing the original toilets, urinals, and lavatories
| MBK | Site | Entrance loop modifications | Capital Renewal | 4 | 1 | 190602 | 154560 |  |  |  | 120000 |  | 120000 | Reconfiguring/repaving the driveway for traffic flow/bussing/walking
| MBK | Site | Perimeter fencing | Capital Renewal | na | 1 | 0 | 10000 |  |  |  |  | 30000 | 30000 | Creating fenced perimeters for age appropriate play areas on the playground
| MBK | Site | Replace Playground Equipment | Capital Renewal | na | 1 | 0 | 30000 |  |  | 40000 |  |  | 40000 | Replace existing elementry playground structures that do not meet current saftey standards
| MBK | Security 1 | Meadowbrook |  | na | 1 | 0 | 57500 |  |  | 35000 |  |  | 35000 | Security upgrade details are confidential
| MBK | Security 2 | Meadowbrook |  | na | 2 | 0 | 57500 |  |  | 27000 |  |  | 27000 | Security upgrade details are confidential
| MBK | Network | Replace/ Upgrade Switches | Capital Renewal |  | 2 | [6 empty] | 7000 | 7000 | Replace and upgrade end of life switches
| MBK | Network | Replace/upgrade Wireless A.P | I.T. End of life | na | 1 |  |  |  |  | 24000 |  |  | 24000 | Replace and upgrade end of life wireless access points
| MBK | Network | Replace /upgrade IP Phones | I.T. End of life | na | 1 |  |  |  |  | 10000 |  |  | 10000 | Replace and upgrade end of life ip phones
| MBK | Specialties | Custodial Equipmet |  | na | 3 | [5 empty] | 10000 | 10000 | 20000 | Replacing /upgrading the District's 20 yr old custodial equipment
|  |  | Meadowbrook School Subtotal | [7 empty] | 242858 | 164500 | 58500 | 465858
|  |  |  | District Wide Grand Total | [9 empty] | 4955814
|  |  | Breakdown | [7 empty] | 3009169 | 772095 | 774550
|  |  | School Security | School Security | [9 empty] | 635000
|  |  | I.T. Infrastructure | I.T. Infrastructure | [9 empty] | 701000
|  |  | Gross Reimbursable Expenditure | Gross Reimbusable Expense | [9 empty] | 4170814
|  |  | Non Reimburseable expenditure | Non Reimburseable Expenses | [9 empty] | 785000